SUPPORT BY IFPRI FOR

fURTHER DEVELOPMENT & TRAINING in minecofin-OCE sam/cge

first Phase [July-OCt] 2024

draft Concept note  (July 4, 2024)

Background

The current MINECOFIN Social Accounting Matrix (SAM) and CGE model—implemented by IFPRI under a GIZ-supported project in 2019-21—require further development of and staff training in these tools. This is crucial for meeting MINECOFIN’s projection and analysis needs, notably for assessing the impact of fiscal policies, for micro-simulating the impact of shocks and policies on households, and for running longer-term (recursive) dynamic simulations.

This first phase of further IFPRI support is a building stone for the extension of the SAM/CGE to incorporate environmental features to capture: the impact of climate change, emissions, mitigation and adaptation measures, and likely other features related to water, land, and forest use and waste/pollution. The second phase—the development of dynamic environmental SAM/CGE—is expected to be implemented by IFPRI with support under a new GIZ-MIP program for 2025-28.

Goal and activities

The goal of this phase ([July-Nov] 2024) is to further develop the SAM/CGE in line with MINECOFIN’s needs, especially incorporating VAT and excises (with exemptions and in/formal segments in each sector) and further Rwanda-specific features in the production functions.

Further development and training activities (including workshops) will cover:

- Updating of the 2017 SAM to a more recent base year (2021 or later) and updating of the household (poverty) module using the most recent household and labor force surveys; adjustment of SAM to VAT and other further modeling needs

- Further adjustment of CGE to Rwanda's needs:

--VAT and excises, incl. exemptions, in/formal, tax expenditure and indirect subsidies

--sector specification (govt services, re-exports,…) and public capital in production functions

- Adjustment of the CGE and programming to enable recursive dynamic simulations

- Training in making changes in model specification in GAMS, including simplifying the GAMS code where possible

- Training in specifying/running a variety of scenarios (in/direct taxes, sector capital stocks, TFP, govt spending, …) and interpreting results, in comparison with results of other CGEs.

MODALITIES, DELIVERABLES AND TIMELINE

The support from IFPRI will be provided via online video sessions, online exchanges, and two on-site 1o days workshops.

Rwandan participants

3 staff of OCE’s modeling group, plus 1-2 interns with CGE experience

1-2 staff/interns from Tax Policy Dept

1-2 counterparts in RRA research dept

1-2 staff from NBR focusing on CGE

possibly 1-2 NDPR/ NISR staff.

| Timetable further development & training SAM/CGE, [July-Oct] 2024 |  |
| --- | --- |
| Timeline | Deliverables |
| Aug 2024 on-line sessions (.. days) | SAM updating: validation of existing/provision of new data explanation and transfer of new SAM CGE adjustment (notably VAT/excise etc. ): explanation and transfer of revised model |
| Sep-Oct 2024 1-2 week on-site workshop | exercises and static simulations with revised SAM/CGE further refinements of model specification changing model specifications in GAMS |
| Aug-Oct 2024 on-line sessions (.. days) | exchanges on further exercises, adjustments, simulations |
| Nov 2024 1-2 week on-site workshop | exercises and dynamic simulations with revised SAM/CGE micro simulations preparing workshop product: tax/fiscal policy scenarios |

Reflecting in part the Nov 2023 World Bank Concept Note on TA for CGE and following meetings between OCE, IFPRI, WB, and GIZ on January 22 and June 10, 2024.