| Revised Plan of Action for Workshops 3-6 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| W/S | Activity | Description | Sub-activities | Time | Date |
| 3. | 2017 SAM Building using the Toolkit (10-day activity) | Learn use the SAM Building Toolkit to construct a new 2017 SAM together with MINECOFIN and NISR. | Recap basics of a SAM and overview of the SAM Toolkit | ½ day | April/May 2020 |
|  |  |  | Macro-SAM building & taxes | 1 day |  |
|  |  |  | Splitting GDP by sector (with workgroups on AGR and IND) | 2 days |  |
|  |  |  | Trade, public finance, & investment data analysis | ½ day |  |
|  |  |  | Household consumption data & Stata analysis | 1 day |  |
|  |  |  | Taxes & transaction cost margins | 1 day |  |
|  |  |  | Balancing the national SAM using cross-entropy | 1 day |  |
|  |  |  | Disaggregating households & factors | 1 day |  |
|  |  |  | Balancing the SAM with disaggregated households | 1 day |  |
|  |  |  | Meeting with MINAGRI and others | 1 day |  |
| 4. | GAMS coding & modeling (10-day activity) | Training on GAMS programming using ‘Lofgren’ exercises, plus in-depth walk- through of IFPRI model equations and GAMS code. Two projects of policy relevance will be identified and assigned to two groups. Trainees will begin data collection, background analysis & scenario design. | Introduction to GAMS as a programing language | ½ day | July 2020 |
|  |  |  | Ex0: Coding a multimarket model in GAMS | ½ day |  |
|  |  |  | Ex1: Closed economy, no-government | 1 day |  |
|  |  |  | Ex2: Adding investment | 1 day |  |
|  |  |  | Ex3: Saving-investment | 1 day |  |
|  |  |  | Ex4: Government | 1 day |  |
|  |  |  | Ex5: Open-economy | 1 day |  |
|  |  |  | IFPRI model equations & structure | 1 day |  |
|  |  |  | GDX importing/exporting of data | ½ day |  |
|  |  |  | Class exercises using GAMS & IFPRI model | 1 day |  |
|  |  |  | Group projects: - Breaking down the problem - Outlining simulations - Implementing scenarios | 2 days |  |

| --------- Refine project topics & collect data & other information until the next workshop -------------- |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 5. | Advanced topics in coding & modeling (10-day activity) | Continued training on CGE modeling, with in-depth training on special topics (order & topics can be adjusted as needed). Continue group projects by finalizing scenarios & learning to present results to a policy audience. | Recap workshop 4 & refresher class exercises | 2 days | Sept. 2020 |
|  |  |  | Topic 1: Modeling tax policy (with class exercises) | 1 day |  |
|  |  |  | Topic 2: Modeling public investments (with class exercises) | 1 day |  |
|  |  |  | Continue group projects: - Review data & background information - Refine simulations - Prepare slides & outline brief - Present to class | 3-4 days |  |
|  |  |  | Topic 3: Dynamic modeling & designing a baseline scenario | 1 day |  |
|  |  |  | Topic 4: Poverty analysis using microsimulation models | ½ day |  |
|  |  |  | Discussion: Linking to existing MINECOFIN models | ½ day |  |
| ----------------------------- Write-up & review project reports until the next workshop --------------------------- |  |  |  |  |  |
| 6. | Study results (3-day activity) | Disseminate their research findings in a seminar. | Recap of workshop 5 | ½ day | Jan. 2021 |
|  |  |  | Dry-run presentations & revisions to scenarios, slides & briefs | 1½ days |  |
|  |  |  | Public presentation of projects | ½ day |  |
|  |  |  | Meetings with MINECOFIN and others | 1 day |  |